|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1)Executive Summary | | | | |
| Project Manager | | Status Date | Phase | |
| *Ryan Meuth* | | 11/10/2020 | Week 8 | |
| Project Status Schedule | Y | Still need to finalize scoring for all games and need to connect games with the front page, we can move on to game review after that. | | |
| Green = Launch On Schedule | Yellow =Tasks Behind Schedule | | | Red = Critical Path Impact |
| Project Document Repository | [Pause Screen Demo](https://editor.p5js.org/nsulliv7/sketches/kQtbG-H-V)  [Line Drawing](https://editor.p5js.org/jlbudd/sketches/7OsiQhYpJ)  [Target Practice](https://editor.p5js.org/anaveed1/sketches/5cHSDZ4vE)  [Guitar Hero](https://editor.p5js.org/nqsullivan/sketches/8zFZvtAOhl)  [Front Page](https://editor.p5js.org/rjkeyser/sketches/l05TQ8Lm7) | | | |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 2) Key Schedule Milestone Tracking from Gantt Chart | | | | |
| Tasks | Target Date | Actual Date | Status (%) | Comments |
| Line Drawing Implementation | 10/27/2020 | 11/10/2020 | 100% |  |
| Target Practice Implementation | 10/30/2020 | 11/10/2020 | 90% | Need to work on scoring |
| Guitar Hero Implementation | 11/02/2020 | 11/10/2020 | 90% | Adding music |
| Line Drawing Review | 11/10/2020 | 11/10/2020 | 60% | Scoring system needs to be less confusing |
| Target Practice Review | 11/12/2020 | 11/10/2020 | 60% | Scoring needs to be finalized |
| Guitar Hero Review | 11/14/2020 | 11/10/2020 | 60% | Need to finish added music |

|  |
| --- |
| 3) Progress from This Week *<should include pending tasks from previous week>* |

* Give Line Drawing game feedback in game
* Give dialogue boxes feedback when hovered
* Added explosions to target practice game
* Have been adding music, making it line up with falling notes and making game speed up the higher score you get

|  |
| --- |
| 4) Progress Planned for Next Week |

* Put all games together though the Front page
* Use [storeItem()](https://p5js.org/reference/#/p5/storeItem) to save high scores

|  |
| --- |
| 5) Gantt Chart Updated *<add the newest Gantt Chart>* |

[Gantt Chart 11/10](https://drive.google.com/file/d/1phhJ6sTV-qU2kDQvNCPElQ9ElEoFhk1t/view?usp=sharing)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 6) Team-Evaluation for the Week | | | | | |
| Team Member Name | Absent | Poor | Fair | Good | Outstanding |
| Abdur Naveed |  |  |  |  | X |
| Joshua Budd |  |  |  |  | X |
| Nathaniel Sullivan |  |  |  |  | X |
| Ryan Keyser | X |  |  |  |  |