## Sheet1
Project Name:
Task | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5 | [5 empty] | Week 6 | [5 empty] | Week 7 | [5 empty] | Week 8 | [5 empty] | Week 9 | [5 empty] | Week 10
| 22/09/20 | [5 empty] | 29/09/20 | [5 empty] | 2020-06-10 | [5 empty] | 13/10/20 | [5 empty] | 20/10/20 | [5 empty] | 27/10/20 | [5 empty] | 2020-03-11 | [5 empty] | 2020-10-11 | [5 empty] | 17/11/20 | [5 empty] | 24/11/20
Milestone 1 Defining the Exercises | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu | W | Th | F | Sa | M | Tu
Defint the type of excerciess | bar: 22/09/20 Tu to 22/09/20 W; 29/09/20 Tu
Define the type of human-computer interaction | bar: 22/09/20 W to 22/09/20 Th; 29/09/20 Tu
Define the three excercises | bar: 22/09/20 F to 29/09/20 Tu
Milestone 2 Animate Shapes
Line Drawing Define Interaction | bar: 29/09/20 Tu to 29/09/20 M; 20/10/20 Tu
Target Practice Define Interaction | bar: 29/09/20 Tu to 29/09/20 M; 20/10/20 Tu
Guitar Hero Define Interaction | bar: 29/09/20 Th to 2020-06-10 Th; 20/10/20 Tu
Line Drawing GUI components | bar: 2020-06-10 Tu to 2020-06-10 M; 20/10/20 Tu
Target Practice GUI components | bar: 2020-06-10 Tu to 2020-06-10 M; 20/10/20 Tu
Guitar Hero GUI components | bar: 2020-06-10 Tu to 13/10/20 Tu; 20/10/20 Tu
Milestone 3 Interact with Shapes
Line Drawing Define feedback | bar: 13/10/20 W to 20/10/20 Th; 2020-03-11 Tu
Target Practice Define feedback | bar: 13/10/20 W to 20/10/20 F; 2020-03-11 Tu
Guitar Hero Define feedback | bar: 13/10/20 W to 27/10/20 Tu; 2020-03-11 Tu
Line Drawing Implementation | bar: 13/10/20 Tu to 27/10/20 Tu; 2020-03-11 Tu
Target Practice Implementation | bar: 13/10/20 Tu to 27/10/20 Th; 2020-03-11 Tu
Guitar Hero Implementation | bar: 13/10/20 F to 2020-03-11 Tu
Milestone 4 Quality Assessment
Line Drawing Review | bar: 2020-03-11 Tu to 2020-10-11 Tu; 17/11/20 Tu
Target Practice Review | bar: 2020-03-11 Th to 2020-10-11 Th; 17/11/20 Tu
Guitar Hero Review | bar: 2020-03-11 Sa to 2020-10-11 Sa; 17/11/20 Tu
Product Demonstration
Line Drawing Polish | bar: 2020-10-11 W to 24/11/20 Tu; 24/11/20 Tu
Target Practice Polish | bar: 2020-10-11 F to 24/11/20 Th; 24/11/20 Tu
Guitar Hero Polish | bar: 2020-10-11 M to 24/11/20 Sa; 24/11/20 Tu